Appendix A: University of Michigan Singapore Students Association Freshmen Welcome Program 2006 Timeline

| S/N | Date | Event | Responsibility | Comments |
| --- | --- | --- | --- | --- |
| 1 | 27 March | 1st committee meeting | OP | Form sub-committees, mailing list |
| 2 | April | Establish contact with Office of Undergraduate Admissions | OP, HR |  |
| 3 | April / May | Filming of Orientation Video Collection of material for presentation | IT | In Ann Arbor |
| 4 | May | Begin program planning | EM, LO |  |
| 5 | May | Establish contact with University of Michigan Alumni Association | HR |  |
| 6 | May | Start sourcing for venues and catering services | LO |  |
| 7 | 3 June | Confirmation of venues | LO |  |
| 8 | June | Formation of mentor groups and peer advising groups | HR |  |
| 9 | June | Obtain name list of incoming freshmen | HR | In Ann Arbor |
| 10 | June | Work on Information Package | EM | In Ann Arbor |
| 11 | June | Updates on SSA website | IT |  |
| 12 | 23 June | End of Spring Half Term 2006 | - |  |
| 13 | 1 July | Establish contact with freshmen | HR |  |
| 14 | 1 July | Confirmation of event concepts | EM, IT |  |
| 15 | 1 July | Confirmation of catering services and equipment list | LO |  |
| 16 | 2 July | Re-union meeting | OP | Updates from all sub-committees |
| 17 | July | Informal group meetings | - |  |
| 18 | 9 July | Send out invitations | HR |  |
| 19 | 22 July (Sat) | Formal welcome | All |  |
| 20 | 23 July (Sun) | E2K6 |  |  |
| 21 | 5 August | Special event | All |  |
|  |  |  | All |  |

| S/N | Date | Event | Responsibility | Comments |
| --- | --- | --- | --- | --- |
| 22 | 11 to 24 August | Receive freshmen in Ann Arbor | HR | Volunteers needed |
| 23 | 24 August | Earliest check-in date for halls | - |  |
| 24 | 25 August | Start of International Orientation | - |  |
| 25 | 26 August to 4 Sept | Administration, shopping | HR | Volunteers needed |
| 26 | 5 Sept | Start of Fall 2006 | - |  |
| 27 | 15 Sept | Senior-Junior Interaction Session | OP |  |
|  | 16 Sept |  |  | Football game @ Notre Dame |
| 28 | 23 Sept | House-warming | OP | Football game vs. Wisconsin |
| 29 | 30 Sept | Birch Run trip | All | Football game @ Minnesota |
| 30 | 16-17 Oct | Fall study break | - |  |

Key:

OP = Overall Planning

HR = Human Resource

LO = Logistics

EM = Events Management

IT = Information Technology

Useful website: http://www.admissions.umich.edu/admitted/internationalstudents.html

Human Resource

| S/N | Deadline | Task | Comments |
| --- | --- | --- | --- |
| 1 | Ongoing | Establish contact with kiasu incoming freshmen | In Ann Arbor |
| 2 | 12 May | Establish contact with Office of Undergraduate Admissions | In Ann Arbor |
| 3 | 19 May | Revise Survival Checklist | In Ann Arbor IMPT: Emergency contact in AA, available transport from airport |
| 4 | 26 May | Obtain list of mentors and peer advising groups | In Ann Arbor |
| 5 | 9 June | Obtain Orientation Package from Office of New Students Program |  |
| 6 | 9 June | Obtain name list of incoming freshmen |  |
| 7 | 23 June | Confirm name list of incoming freshmen (by phone calls) | In Singapore IMPT: Inform freshmen about UMSSA website |
| 8 | 23 June | End of Spring Half Term 2006 |  |
| 9 | 30 June | Final design of invitation cards Formation of mentor groups Set up umich mailing list with incoming freshmen |  |
| 10 | 2 July | Re-union meeting | Updates from all sub-committees |
| 11 | 3 July | Print out invitation cards | Budget: USD$75 |
| 12 | 7 July | Send out invitation cards |  |
| 13 | 20 July | Ensure each mentor group has met at least once |  |
| 14 | 22 July (Sat) | Formal welcome |  |
| 15 | 23 July (Sun) | E2K6 |  |

Logistics

| S/N | Deadline | Task | Comments |
| --- | --- | --- | --- |
| 1 | 2 June | Confirm formal venue and catering service | Budget: USD$200 |
| 2 | 9 June | Confirm informal venue | Budget: USD$250 |
| 3 | 1 July | Confirm equipment list for formal and informal | Budget: USD$50 |
| 4 | 2 July | Re-union meeting | Updates from all sub-committees |
| 5 | 22 July (Sat) | Formal welcome |  |
| 6 | 23 July (Sun) | E2K6 |  |

Event Management

| S/N | Deadline | Task | Comments |
| --- | --- | --- | --- |
| 1 | May | Link up with Logistics to find out venue constraints |  |
| 2 | 26 May | Confirm program for formal | In Ann Arbor Refer to Ctools for format |
| 3 | 9 June | Confirm program for informal | In Ann Arbor (ideas from everyone) |
| 4 | 23 June | End of Spring Half Term 2006 |  |
| 5 | 2 July | Re-union meeting | Updates from all sub-committees |
| 6 | 22 July (Sat) | Formal welcome |  |
| 7 | 23 July (Sun) | E2K6 |  |

IT

| S/N | Deadline | Task | Comments |
| --- | --- | --- | --- |
| 1 | 19 May | Complete filming of Orientation Video | In Ann Arbor |
| 2 | 26 May | Complete editing of Orientation Video | In Ann Arbor |
| 3 | 3 July | Updates on SSA website | Program/venue for formal and informal |
| 4 | 2 July | Re-union meeting | Updates from all sub-committees |
| 5 | 22 July (Sat) | Formal welcome |  |
| 6 | 23 July (Sun) | E2K6 |  |

Overall Planning

| S/N | Deadline | Task | Comments |
| --- | --- | --- | --- |
| 1 | 19 May | Establish contact with University of Michigan Alumni Association | Liheng |
| 2 | 2 July | Re-union meeting | Updates from all sub-committees |
| 3 | 4 July | Send e-mails to freshmen regarding formal and informal | Chee Chian |
| 4 | 14 July | Set up freshmen mailing group | Jun Rong |
| 5 | 22 July (Sat) | Formal welcome |  |
| 6 | 23 July (Sun) | E2K6 |  |